## Project Completeness
Overall Progress Report for NHLBI Contract - Biweekly Report Sent on Fridays | [7 empty] | Completeness of the Project (%) |  | 7.59
Contract # | HHSN268201600038I/HHSN26800002 |  |  |  | CORE Year 3 |  |  | Total # of samples approved |  | 20000
Center Name |  |  |  |  | Form Ver 3.0 |  |  | Total # of samples completed |  | 1518
Week of | 2018-07-01
Study/Cohort | MTA needed? | Submission | Expected Date of First Shipment | Expected Date of Final Shipment | Approved Sample Number | Total Samples Received To Date | DNA QC Pass | DNA QC Fail | Bisulfite Intake | Bisulfite QC |  | Array Processing Intake | Array QC Failed (Rehyb) | Array QC Pass (98% with p<0.05) | Average Completeness |  | Data Processed (LEVEL1/2/3) | Data Uploaded | IRC/DCC Notified
[10 empty] | In Process | Pass |  |  |  | (p<0.05) | (p<0.01)
Study/Cohort 1 | no | Initial | 2018-11-26 |  | 2900 | 2440 | 866 | 14 | 866 | 384 | 383 | 384 |  | 383 | 0.99939 | 0.99923 | 383 | 383 | 383
Replacement
Study/Cohort 2 | no | Initial | 2018-01-19 |  | 9700 | 2279 | 279 | 0 | 279 | 279 | 248
Replacement
Study/Cohort 3 | no | Initial | 2018-02-17 | 2018-05-28 | 1200 | 1200 | 1200 | 0 | 1200 | 996 | 996 | 960 |  | 960 | 0.99936 | 0.99924 | 960 | 960 | 960
Replacement
Study/Cohort 4 | no | Initial | 2018-03-25 | 2018-06-11 | 3200 | 1700 |  |  | 0 |  |  | 90
Replacement
Study/Cohort 5 | no | Initial | 2018-03-25 | 2018-05-29 | 3000 | 2301 | 2190 | 3 | 187 | 187 | 186 | 176 | 1 | 175 | 0.99953 | 0.99933 | 175 | 175 | 175
Replacement
HapMap CEU - NA12878
HapMap CEU - NA12878
HapMap CEU - NA12878
Total |  |  |  |  | 20000 | 7619 | 4535 | 17 | 2532 | 1846 | 1813 | 1610 | 1 | 1518 | 0.99938 | 0.99925 | 1518 | 1518 | 1518
Outstanding or Critical Issues:
Study 1, 3, 4, and 5 studies have all reagents (tubes/racks/caps) to plate and ship samples and Study 2 has 50% of the total of reagents. Study 3 has missed last two promissed ship dates. | [5 empty] | High failure rate of Study 2 DNAs will require cleanup of all existing DNA samples to remove trace histone protein contamination.

## Metrics Definitions
Metric Name | Metric definition
External ID | TOE ID Provided by Study Site
Study/Cohort | Study Site
Batch | Internal Batch designation - Matches download batch on FTP site
DNA QC | QC Status for DNA amount/concentration
Bisulfite QC | QC Status for post-bisulfite conversion
Detected Assays (P<0.05) | Number of assays with data above background level with a p value less than 0.05
Detection Completeness (p<0.05) | Fraction of assays with data above background level with a p value less than 0.05
Detected Assays (P<0.05) | Number of assays with data above background level with a p value less than 0.01
Detection Completeness (p<0.05) | Fraction of assays with data above background level with a p value less than 0.01
Array QC | QC Status for Array Data (based on Fraction of assays with data above background level with a p value less than 0.05): >=0.98 is pass; Failed samples will not be included in any data uploads

## Production Metrics
External ID | Study/Cohort | Batch | DNA QC | Bisulfite QC | Detected Assays (P<0.05) | Detection Completeness (p<0.05) | Detected Assays (P<0.05) | Detection Completeness (p<0.05) | Array QC
TOE123 | Study 1 | B0001 | Pass | Fail | 101654 | 0.11737 | 48047 | 0.055476 | Fail
TOE760 | Study 1 | B0001 | Pass | Pass | 865661 | 0.9995 | 865538 | 0.99936 | Pass
TOE820 | Study 1 | B0001 | Pass | Pass | 865352 | 0.99915 | 865183 | 0.99895 | Pass
TOE667 | Study 1 | B0001 | Pass | Pass | 865332 | 0.99912 | 865163 | 0.99893 | Pass
TOE219 | Study 1 | B0001 | Pass | Pass | 865257 | 0.99904 | 865048 | 0.9988 | Pass
TOE143 | Study 1 | B0001 | Pass | Pass | 865667 | 0.99951 | 865533 | 0.99936 | Pass
TOE232 | Study 1 | B0001 | Pass | Pass | 865365 | 0.99916 | 865094 | 0.99885 | Pass
TOE460 | Study 1 | B0001 | Pass | Pass | 865643 | 0.99948 | 865516 | 0.99934 | Pass
TOE069 | Study 1 | B0001 | Pass | Pass | 865377 | 0.99918 | 865238 | 0.99902 | Pass
TOE334 | Study 2 | B0002 | Pass | Pass | 865683 | 0.99953 | 865507 | 0.99933 | Pass
TOE182 | Study 2 | B0002 | Pass | Pass | 152630 | 0.17623 | 84616 | 0.097699 | Fail

## Project Averages
Project | Percent Completeness (p<0.05) | Percent Completeness (p<0.01)
Study/Cohort 1 | 99.94% | 99.92%
Study/Cohort 2 | #DIV/0! | #DIV/0!
Study/Cohort 3 | 99.94% | 99.92%
Study/Cohort 4 | #DIV/0! | #DIV/0!
#REF! | #REF! | #REF!

## Doc Versioning
Authored by GJP
Original version by George J Papanicolaou, PhD
Version Changes
3.0 Finalized by GJP 08/01/2019
2.1 Modified for Methylation Profiling -dvdb- 05/03/2017
2.0 Added example reports, provided additonal production metrics, and introduced Project Averages tab -gjp- 6/29/2017
1.0 Released 2/10/2017