## Project Completeness
Overall Progress Report for NHLBI Contract - Weekly Report Sent on Fridays | [8 empty] | Completeness of the Project (%) |  | 41.4664
Contract # | [5 empty] | CORE Year 1 |  |  | Total # of samples approved |  | 4910
Center Name | [5 empty] | Form Ver 2.0 |  |  | Total # of samples completed |  | 2036
Week of
Study/Cohort | MTA needed? | MTA in place? | Confirmation from study - shipping only samples from blood with dbGaP consent | Expected Date of First Shipment | Expected Date of Final Shipment | Approved Sample Number | Total Samples Received To Date | DNA QC Pass | DNA QC Fail | Sample Intake | Sequencing or post-sequencing QC in progress |  |  | Completed sequencing and post-sequencing QC | Failed sequencing or post-sequencing QC (will not re-attempt) | BAMs Awaiting Transmission to IRC | BAMs Transmitted to IRC | Expected BAM Submission completion date
[11 empty] | Library | Sequencing | Mapping
Study A | yes | yes | yes | 2015-10-21 | 2015-10-21 | 650 | 636 | 636 | [5 empty] | 636 | 0 | 0 | 636 | complete
Study B | no | N/A | yes | 2016-01-20 | 2016-03-30 | 2400 | 2773 | 2585 | 188 | 1063 | 185 | 98 |  | 1054 | 0 | 0 | 900 | pending release
Study C | yes | yes | yes | 2016-02-01 | TBD (replacements) | 1860 | 1872 | 1803 | 69 | 159 | 2 | 9 | 79 | 1554 | 0 | 1054 | 500 | TBD
HapMap CEU - NA12878
HapMap YRI - NA19238
PUR trio
Total | [5 empty] | 4910 | 5281 | 5024 | 257 | 1222 | 187 | 107 | 79 | 3244 |  | 1054 | 2036
Outstanding or Critical Issues:
Unassigned Study A samples = samples not yet identified + samples for which we don't yet have a manifest + samples that don't have Institutional Certification yet: | [8 empty] | Study B concentration errors led to a higher than normal QC failure rate. The issue has been resolved and we expect to get sample replacements for most of the 188 failed samples. |  |  |  |  | As discussed with COR, due to a reagent issue at Company Z production is lower than expected. This will continue to be the case until Z tests and manufactures replacement reagents to correct the problem. We are monitoring the situation daily and will be able to test a replacement reagent soon--before it moves to manufacturing.
1. Children's/Smith/100 cases and 100 controls | [13 empty] | 2/12 Update: We tested a small batch of replacement reagents, which fixed the problem; the data look good. But Z will not have more of the new reagent for several weeks. Therefore, production will continue to be lower than expected until we receive replacement reagents.
2. Chicago State/Jones/118 samples
Due to network issues, CRAM transmission to IRC has been reduced by half. Expected completion 2/28.

## Metrics Definitions
Metric Name | Metric definition
PF HQ Aligned Q20 Bases | The subset of PF_HQ_ALIGNED_BASES where the base call quality was Q20 or higher | Examples
Mean Insert Size (Library AVG) | The mean insert size of the "core" of the distribution
Contamination % | The overall aggregate percent contamination estimate
mean coverage (raw) | The mean coverage in bases of the genome territory, after all filters are applied.
WGS HET SNP Q | The metric that attempts to predict the probability of not finding a (heterozygous) SNP variant in the data (in Phredscale)
WGS HET SNP SENSITIVITY | The metric that attempts to predict the probability of finding a (heterozygous) SNP variant in the data
This field will contain contract required, center recommended, as well as % contaimation output script created by TOPMed IRC

## Production Metrics
External ID | Collection | PF HQ Aligned Q20 Bases | Mean Insert Size (Library AVG) | Mean Coverage (Raw) | WGS HET SNP Q | WGS HET SNP SENSITIVITY | Per 10 Coverage Bases | Per 20 Coverage Bases | Q20 Bases | Contamination % | Notes
ABC123456 | PI (Location) - Study Acronym | 1234567890 | 401 | 36 | 16 | 95 | 99.04 | 98.31 | 129015533517 | 2.709% | *contamination over 1%
Will contain output for at least the last 4 weeks along with metrics. Make sure to use DCC tracking IDs in column A

## Project Averages
Project | Avg. Median Insert Size | Average Coverage | Avg. Per 10 Coverage Bases | Avg. Per 20 Coverage Bases | Avg. Q20 Bases | Avg. % Contam (Verify Bam ID)
Study A | 420.4722 | 38.7159 | 99.2028 | 97.2668 | 117440034638.833 | 0.0013528
Study B | 406.2387 | 39.3739 | 99.0781 | 96.6291 | 119531174840.991 | 0.00070095
Study C | 424.2437 | 38.0801 | 99.598 | 95.8398 | 116816823948.336 | 2.709

## Doc Versioning
Authored by GJP
Original version by George J Papanicolaou, PhD
Version Changes
2.0 Added example reports, provided additonal production metrics, and introduced Project Averages tab -gjp- 6/29/2017
1.0 Released 2/10/2017